Neighbourhood Planning Meeting

05/04/2023

Minutes

Attended:

Julian Campbell

Sue French

Lesley Osbourne

Chris Hall

Michelle Ferris

Don Macbean

Apologies

Dan Smith

- The Draft plan booklets and consultation comment sheets were delivered by Ian today with a copy of the landscape appraisal report and urban design document. A draft of the Local Green Space Appraisal has been circulated online for the group to comment before printing.

- The documents will be uploaded onto the PC website by April 11th for the start of the public consultation period. This ends on May 30th. The public comments will be collated online and in paper format – combined into the online survey and then the final draft will be amended where necessary before submission to WSC.

ACTION – Julian will update the website and add the information and links for the consultation by April 11th. Julian will signpost residents to the previous information that was delivered with The Pump.

ACTION – Sue will create a poster to signpost the public to the website and put the draft plans into the three locations in the village where the public can read the plan and be directed to paper copies if necessary. (Chris will hold paper copies)

Draft plan booklets can be borrowed for five days and checked out and in by Chris.

ACTION - Ian will liaise with Joanna to inform the statutory consultees.

- The Drop-In on April 15th runs from 10.00 – 1.00pm.

9.15 – 11.30 – Lesley, Sue, Chris, Michelle to set up and attend

11.30 – 1.30 – Don, Julian, Chris and Michelle to close

Tea bags – Sue,  Coffee  -  Don, Cake  - Michelle, Milk / Sugar – Lesley

Ian will deliver the boards and further evidence documents at 9.30. Tables will need to be laid out as before.

- The group spent time considering the contents of the Local Green Spaces Appraisal. A list of amendments was distributed to the group by S.F. Ian has suggested that any changes should be made after the consultation and before submission to WSC.

- Ownership of several designated green spaces have yet to be identified. The parish clerk will be approached for assistance.

Next meeting – June 14th 7.30 at Chris Hall’s house, many thanks for your hospitality!